The following timeline is a guide for faculty seeking approval from WORLD to lead programs abroad. The timeline and associated procedures assist faculty and WORLD to:

- Execute internal and external logistics for programming and budgeting.

- Identify and forecast risk and risk management protocols, and responsibility associated with (group) travel in non-U.S. locations.

- Apply protocols and policies to ensure student safety and security.

- Integrate standards for high-impact engagement abroad using Forum on Education Abroad’s Standards of Good Practice for Education Abroad and the Code of Ethics for Education Abroad.

- Align student learning outcomes and teaching learning outcomes with geographically/culturally appropriate locations.

- Evaluate elements of global learning using best practice framework.

- Market the course, program, or activity to recruit students effectively.

STETSON UNIVERSITY’S COMMITMENT TO STUDY ABROAD

Stetson University offers Faculty-Led Study Abroad over the course of the academic year, ranging from winter and Spring Break offerings to courses over multiple weeks during May-July. As a high-impact practice, Study Abroad promotes global learning, the process of diverse people analyzing and addressing complex problems that transcend borders. In turn, global learning nurtures habits of mind of global citizens – global community engagement, diversity and inclusion, environmental responsibility, and social justice. Global Citizenship is a core value of Stetson University's mission to prepare students to be informed, active, and engaged citizens of both local communities and the world.

A GLOBAL CITIZEN

- Articulates their own values in the context of personal identities and recognizes diverse and potentially conflicting positions vis-à-vis complex social and civic problems [AWARENESS]

- Understands the interactions of multiple worldviews, experiences, histories, and power structures on an issue or set of issues [UNDERSTANDING]

- Gains and applies deep knowledge of the differential effects of human organizations and actions on global systems [APPLICATION]

- Applies knowledge and skills gained through general education, the major, and co-curricular experiences to address complex, contemporary global issues [APPLICATION]

- Initiates meaningful interaction with people from other cultures in the context of a complex problem or opportunity [ACTION]

- Takes informed and responsible action to address ethical, social, and environmental challenges [ACTION]

The ideal timeline initiates at least one year prior to implementation of the faculty-led program.

MONTH 13 (MAR):	WORLD hosts Lunch & Learn: How to Plan and Fund a Study Abroad Program

  - Faculty participate in discussion with WORLD staff and experienced Study Abroad faculty on developing and implementing international courses and programs: proposal/approval processes, financial modeling, risk management, marketing, etc.  Webinars are also held throughout the summer leading up to the proposal deadline

MONTH 12-8 (APR-AUG):	Faculty meets with WORLD staff to discuss program

  - Faculty and WORLD staff discuss proposed course, location, dates, activities in proposed location to enhance/complement the academic content, budget, and marketing/recruitment plan – Faculty complete program questionnaire

  - Faculty and WORLD staff discuss Study Abroad Approval Process and deadlines

  - Faculty submits program description and syllabus to academic unit(s) for approvals (per process in academic units process):

    - College of Arts & Sciences: Proposal review by school/college curriculum committee (dean sits on committee as ex officio member)

    - See IUPUI Taxonomy as example for assessing Study Abroad courses and learning experiences.

  - WORLD sends program bids to at least 2-3 providers (if applicable)

  - WORLD receives provider proposal bids (about 3-4 week timeframe to receive)

  - Faculty reviews bids to determine best fit for their course

  - WORLD initiates contract vetting and approval process

  - Faculty and WORLD staff draft, review, and edit program budget after proposals are received to include provider program costs.

MONTH 11-7 (MAY-SEPT):	Deadline for online Faculty-Led Study Abroad Application:

Spring & Summer - New Programs: May 30th 	Recurring programs: June 13th 
Fall & Winter – New Programs: March 15th   	Recurring programs: April 1st

  - Faculty member initiates online Study Abroad application in Terra Dotta

    - basic program logistics (dates, location, number of students, etc.)

    - proposed abroad course

    - description and syllabus

    - how program location enhances the academic content

    - alignment with Stetson’s mission and core values

    - proposed budget

  - WORLD receives formal approval from department chair and college/school dean completes application process

    - College of Arts & Sciences: Curriculum committee representative submits note of formal approval to WORLD

  - WORLD staff reviews online application to ensure consistency with guiding principles: proposed program is safe, compliant, financially sound, and realistic

MONTH 8-6 (AUG-Oct):	WORLD provides written approval of proposed program

  - WORLD vets provider contract with Stetson Risk Management and Legal

  - Provost endorses provider contract

  - WORLD develops marketing materials to promote the program with support of Faculty member including program page on Terra Dotta

  - WORLD assists faculty with marketing and recruitment strategies including information and classroom sessions

  - WORLD creates customized online student application in Terra Dotta

  - WORLD provides faculty with access to student application submissions

  - Faculty leaders to participate in Global Citizenship Fair held on Values Day for program promotion

  - Students apply for Spring/Summer international learning scholarships (deadline October 1)

MONTH 5-1 (Nov-Apr):	WORLD provides other administrative/logistical support

  - WORLD manages/revises Study Abroad program budget with support of Faculty member

  - Faculty member continues to actively promote and recruit students for the program. This includes classroom presentations across the department, information sessions, direct email, and social media.

  - WORLD completes Disciplinary Record Checks on all applicants

  - Faculty member reviews and renders admission decisions on program applications

  - Faculty member provides communication support and reaches out to students with assistance from WORLD for students to complete application, submit deposit and final payments, complete post acceptance forms, etc.

  - WORLD collects student deposits and payments

  - WORLD pays program providers upon receipt of invoices.

  - Students apply for Summer/Fall international learning scholarships (deadline February 1)

  - WORLD requests cash advance and stipend payment for faculty

  - WORLD hosts pre-departure orientation for students; reviews Study Abroad Handbook

  - WORLD hosts pre-departure orientation for faculty; reviews Faculty-Led Study Abroad Handbook

Post Program:	Program Wrap Up

- Faculty submit original receipts for expenses paid during program to WORLD for reimbursement including tolls, parking, home address for mileage, etc. – WORLD staff submits final budget to Finance for reimbursement and budget reconciliation

- WORLD sends students post program evaluation

- Faculty Member completes program evaluation and debriefs with WORLD staff.